## Events & Deliverables
Basic Information about the event | As for | [6 empty] | Deliverables |  | Budget
Proposer(s) | e-mail(s) | co-orgaizers & e-mails | Title of meeting | Start date | End date | City | Country | Deliverable, Objective | The status/progress of the deliverable | Budget top-up: Is it fine? Is it ok to spend it?
Codruta Mare | codruta.mare@econ.ubbcluj.ro; codruta.mare@gmail.com |  | Diversity challenges and stackeholders' engagement | 2023-02-01 | 2023-02-02 | Cluj-Napoca | Romania | 2. Report on good examples and best practices for a transparent finance industry with guidelines to improve transparency | The report has been accepted for publication in Open Research Europe
Alla Pethukina | alla.petukhina@htw-berlin.de |  | Data science for sustainable economics and finance | 2023-08-28 | 2023-09-01 | Berlin | Germany | 8. Position papers, aimed at regulators and policy-makers, on methodology (with examples of formal criteria) for testing AI techniques in real-time
Alessandra Tanda | alessandra.tanda@unipv.it | CO-ORG WITHIN COST ACTION: Maria Elena De Giuli elena.degiuli@unipv.it; Claudia Tarantola claudia.tarantola@unipv.it , Alberto Citterio alberto.citterio@uninsubria.it(ITALY); Ana Ivanisevic Hernaus aivanisev@net.efzg.hr (CROATIA); Bernardo P. Marques, bmarques@ucp.pt (PORTUGAL); Thomaidis Nikolaos, nthomaid@econ.auth.gr (GREECE); Alessia Paccagnini alessia.paccagnini@ucd.ie (IRELAND); Timothy King, timothy.king@uwasa.fi (FINLAND) + Ellen Pei-yi Yu (UK - is in the process of joining the CA19130) | Diversity challenges for a sustainable Fintech | 2023-04-13 | 2023-04-14 | Pavia | Italy | 4. A database which contains data on crowdfunding/P2P platform features useful for rating platform integrity and to predict fraud | I think it is already ready (ref. Branka https://drive.google.com/drive/folders/1qJmo2T0VeOojtC4037mmukyaElP2IGNP) + an excel file with some p2p details (need to be shared in a common platform. Quantinar?) | I'd request additional members joining the conference from ITC to be included in the list of eligible people. Will talk to Branka
Elda Xhumari, Suela Maxhelaku, Endri Xhina | elda.xhumari@fshn.edu.al; suela.maxhelaku@fshn.edu.al |  | Fintech and AI in Finance: Training School for the latest technologies and upcoming challenges | 2023-04-26 | 2023-04-28 | Tirana | Albania | 10. A position paper and roadmap on mitigating risks connected with the increased use of digital assets | In progress
Joerg Osterrieder | joerg.osterrieder@bfh.ch |  | COST FinAI Meets Brussels | 2023-05-15 | 2023-05-16 | Brussels | Belgium | 10. A second position paper and roadmap on mitigating risks connected with the increased use of digital assets Obj 3. To receive input from regulators and practitioners' communities and to validate results with regard to increasing transparency of artificial intelligence applications.
Alessandra Tanda (on behalf of diversity team) | alessandra.tanda@unipv.it | Catarina Silva (catarina@dei.uc.pt), Bernadete Ribeiro (bribeiro@dei.uc.pt), Joana Matos Dias (joana@fe.up.pt) (PT) Albulena Shala (KX) Alessandra Tanda alessandra.tanda@unipv.it Claudia Tarantola claudia.tarantola@unipv.it (IT) Codruta Mare (Romania) Hanna Kristín Skaftadóttir (Iceland) Maria Iannario Roman Matkovvskyy (France) Vassilios Papavassiliou (Ireland) | Women in Fintech and AI (3rd edition) | 2023-06-01 | 2023-06-02 | Coimbra | Portugal | 1. Strategy to engage stakeholders in the Action (including revisions in month 24 and 36) | Included speakers in events from the industry
Peter Schwendner / Marcus Wunsch | scwp@zhaw.ch;wuns@zhaw.ch |  | Transparency of Digital Asset Investments | 2023-05-26 | 2023-05-26 | Winterthur | Switzerland
Vasile Alecsandru Strat | vasile.strat@bbs.ase.ro |  | Fintech companies and regulators in CA19130 | 2023-06-16 | 2023-06-16 | Bucharest | Romania
Joerg Osterrieder | joerg.osterrieder@utwente.nl |  | Risks and Digital Assets | 2023-06-12 | 2023-06-16 | Enschede | Netherlands | 13. Four annual reports (for lay audience) distributed via local and national media
Maria Moloney, Alessia Paccagnini, Valerio Poti | maria.moloney@ucd.ie; alessia.paccagnini@ucd.ie; valerio.poti@ucd.ie |  | ML, AI and Data Protection in Fintech Conference | 2022-07-07 | 2022-07-09 | Dublin | Ireland | 8. Position papers, aimed at regulators and policy-makers, on methodology (with examples of formal criteria) for testing AI techniques in real-time |  | Would benefit from top up for LOS
Petre Lameski/ Joerg Osterrieder | lameski@finki.ukim.mk;joerg.osterrieder@utwente.nl |  | Fintech and AI in Finance | 2023-07-10 | 2023-07-11 | Helsinki | Finland | 11. Methodological discussion paper on the design of stress tests for the evaluation of AI and ML models under shifting financial conditions to improve the robustness of models
Maria Iannario | maria.iannario@unina.it |  | Advanced Statistical Modelling for Fintech, financial inclusion and inequality | 2023-09-13 | 2023-09-15 | Naples | Italy | 5. A discussion paper for possible approaches to building a statistically valid back-testing framework. 10. Methodological discussion papers on AI models to generate “failed trials” of investment product producers and on quantitative strategies with the usage of the promising field of network data analysis exchanges and regional consolidation platforms optimised for accessibility to all partners
Joerg Osterrieder/ Branka Hadji Misheva | joerg.osterrieder@bfh.ch; branka.hadjimisheva@bfh.ch |  | Annual Fintech and AI in Finance MC Meeting | 2023-09-27 | 2023-09-29 | Bern | Switzerland | 15. An edited volume containing scientific achievements of the Action
Please send a request to the entire COST network in case 5 COST countries are not yet involved!
Link to the new budget-plan: https://docs.google.com/spreadsheets/d/1gRIlgHeCxbjKMj8SMboDHVYiwIunwcUB/edit?usp=sharing&ouid=116606579914288490118&rtpof=true&sd=true
2023.02.22 CA19130 -Budget Top Up Request Spring 2023.xlsx

## Status of Deliverables
Deliverlables | Name | Event to deliver
|  | Title of meeting | Start date | End date | City | Country | Status | URL
1 | A database which contains pre-ICO documentation and post-ICO performance (ROI and lifespan)
2 | A database which contains data on crowdfunding/P2P platform features useful for rating platform integrity and to predict fraud | Diversity challenges for a sustainable Fintech | 2023-04-13 | 2023-04-14 | Pavia | Italy | I think it is already ready (ref. Branka https://drive.google.com/drive/folders/1qJmo2T0VeOojtC4037mmukyaElP2IGNP) + an excel file with some p2p details (need to be shared in a common platform. Quantinar?) | https://drive.google.com/drive/folders/1qJmo2T0VeOojtC4037mmukyaElP2IGNP
3 | Discussion papers (DP) on the methodology for evaluating/rating ICOs and crowdfunding/P2P platforms and for detection/early warning about fraud/illegal behaviour with emphasis on the application of AI tools
4 | A position paper and roadmap on mitigating risks connected with the increased use of digital assets | Fintech and AI in Finance: Training School for the latest technologies and upcoming challenges | 2023-04-26 | 2023-04-28 | Tirana | Albania | In progress
|  | COST FinAI Meets Brussels | 2023-05-15 | 2023-05-16 | Brussels | Belgium
5 | A discussion paper for possible approaches to building a statistically valid back-testing framework | Advanced Statistical Modelling for Fintech, financial inclusion and inequality | 2023-09-13 | 2023-09-15 |  | Italy
6 | Methodological discussion paper on the design of stress tests for the evaluation of AI and ML models under shifting financial conditions to improve the robustness of models
7 | Position papers, aimed at regulators and policy-makers, on methodology (with examples of formal criteria) for testing AI techniques in real-time | Data science for sustainable economics and finance | 2023-08-28 | 2023-09-01 | Berlin | Germany
|  | ML, AI and Data Protection in Fintech Conference | 2022-07-07 | 2022-07-09 | Dublin | Ireland
8 | Report on good examples and best practices for a transparent finance industry with guidelines to improve transparency | Diversity challenges and stackeholders' engagement | 2023-02-01 | 2023-02-02 | Cluj-Napoca | Romania | The report has been accepted for publication in Open Research Europe
9 | An internal database of collected (scraped) financial time series from exchanges and regional consolidation platforms optimised for accessibility to all partners
10 | Methodological discussion papers on AI models to generate “failed trials” of investment product producers and on quantitative strategies with the usage of the promising field of network data analysis | Fintech and AI in Finance | 2023-07-10 | 2023-07-11 | Helsinki | Finland
|  | Advanced Statistical Modelling for Fintech, financial inclusion and inequality | 2023-09-13 | 2023-09-15 | Naples | Italy
11 | Four annual reports (for lay audience) distributed via local and national media | Risks and Digital Assets | 2023-06-12 | 2023-06-16 | Enschede | Netherlands
12 | Key software (codes, packages) developed by each of the Working Groups in line with their objectives
13 | Handbook and/or wiki page describing potential approaches to tackle risk management issues related to blockchain assets and crowdfunding/P2P lending
14 | An edited volume containing scientific achievements of the Action (dummy text to delete) | Annual Fintech and AI in Finance MC Meeting | 2023-09-27 | 2023-09-29 | Bern | Switzerland
15 | Strategy to engage stakeholders in the Action (including revisions in month 24 and 36) | Women in Fintech and AI (3rd edition) | 2023-06-01 | 2023-06-02 | Coimbra | Portugal | Included speakers in events from the industry